## Slide 1: Cambridgeshire & Peterborough Healthier Together
Project Kick-Off
Author: Megan Cooper
Date: 19th January 2023

## Slide 2: Background
Cambridgeshire & Peterborough Healthier Together have chosen Frank to design and build their Public Facing Website solution.
Following the completion of the Scoping phase and handover to the Frank studio this pack, for the benefit of both parties, will clarify the following:
  Main Areas of Scope
  Areas Out of Scope
  Roles & Responsibilities
  Open Actions
  Planning Approach
  Milestones
  Change Control
  Project Tools
  Retrospective
  Outstanding Discussion/Decision
  Glossary of Terms
  Frank Contact Details

## Slide 3: Main Scope
Copy site from SYB HT
Template updates & logo
SMS set up and 15k of text credits
Show & Tell including Training
Google Analytics
Annual Hosting for 3 Years
18hrs Support Per Annum
*For full scope please refer to the project brief

## Slide 4: Out of Scope
Content upload by FS
SSL Certificate – FS can supply @ £240 + VAT for 2 years
Any other items not mentioned within the project brief

## Slide 5: Roles & Responsibilities – CP HT
Role | Responsibility
Main contact: Bhesme Nimo | All communication into Frank to flow through these persons. Deliver all open actions against the agreed milestones (see open actions & milestone slides) Gather and manage risks/issues Provide regular updates regarding internal task progression The person can be changed for the different project phases
Escalation contact/ Business Owner: Bhesme Nimo | Escalate any decisions which the ‘Main Contact’ does not have delegated authority to make Decisions to be made in a timely manner – Time to be determined on a case by case basis Co-ordinate further escalation where required Liaise with the Frank 1st Tier escalation contact – Megan Cooper
Testing co-ordinator: Bhesme Nimo | Planning the User Acceptance Testing phase 1st line triage of raised defects – Ensuring that all raised defects are defects/in scope requirements prior to raising with Frank Support with CMS questions (following training) prior to raising with Frank

## Slide 6: Roles & Responsibilities – Cont.….
Role | Responsibility
Training co-ordinator: Bhesme Nimo | Planning the training session Ensure that the training room has the necessary hardware available to Frank (N/A for this delivery) Internal knowledge transfer following the training session (N/A for this delivery)
Implementation Manager Bhesme Nimo | Manage the overall planning of the deployment to Inc. Liaison with the Frank Implementation Manager Planning the launch Internal communication of the deployment Planning and co-ordination of post go live verification Gathering input for the retrospective meeting

## Slide 7: Roles & Responsibilities – Frank
Role | Responsibility
Main contact/PM: Megan Cooper | All communication into CP HT to flow through these persons. Manage the schedule of work along with regular updates on progression Gather and manage risks/issues Manage the Frank implementation tasks The person can be changed for the different project phases
Escalation contact: 1st Tier – Megan Cooper 2nd Tier – Mike Smith 3rd Tier – Jamie Wise | Point of contact for any decisions which the ‘Main Contact’ does not have delegated authority to make Decisions to be made in a timely manner – Time to be determined on a case-by-case basis Co-ordinate further escalation CP HT 1st Tier escalation contact – Bhesme Nimo
Developer: Harry Gopsill | Build the Public Facing in line with the agreed scope and requirements Raise any risks and issues Provide regular progression updates to the Frank PM Support the CP HT Testing co-ordinator, providing timely fixes for defect re-tests Prepare for and facilitate the training session Prepare and execute the promotion of the site into production Inc. google analytics instructions to set up in the dashboard

## Slide 8: Open Actions
No | Description | Owner | Comment | Due Date
1 | Client Resources | FS | Provide Client Resources URL | See milestones
2 | Social Media | CP HT | Provide social media handles | See milestones
3 | Service search | CP HT | Confirm regions for the find a service search | See milestones
4 | Feedback Form | CP HT | Provide default email address for feedback form. | See milestones
5 | Domain | CP HT/FS | Supply domain name – e.g. CPHT-healthiertogether.nhs.uk FS to supply for the NHS DNS team and for the domain to be set up for www & Non-www URL’s | See milestones
6 | SMS Credits | FS | Set up 15K of text credits with Text Local | Part of build
7 | SSL Certificate | CP HT/FS | Confirm if FS are to supply the SSL along with a PO# for invoicing OR CP HT IT team to supply the certificate and keys information | See milestones
8 | Accessibility | FS | FS will require 1 day post content upload to complete the accessibility checks due to the small number of sections going live (See action No.7) | See milestones
9 | IP address | FS | Liaise with the NHS DNS team should the server be ready post CP HT registration or provide IP if available for the initial registration | See milestones
10 | Content upload timeline | CP HT | Discuss length of time required for the content upload to allow the TBC tasks in the milestones slide to be confirmed | See milestones

## Slide 9: Planning Approach
Frank will use an agile approach to delivery – Should client milestones not be met FS will continue with the build and train on how to upload/administer remaining assets.
Scoping phase has been completed.
Frank to copy the SYB HT site and provide this to CP HT along with a show and tell of the site and Training.
Post training CP HT to commence with content amends whilst FS continue to make the necessary amends for the CP HT designs and system checks to the demo site in parallel. Any support required during this period may impact the delivery dates on the milestone slide. This risk is to agreed and accepted by CP HT.
FS will hand the site into formal UAT once the development changes have been completed.
CP HT to hand the ‘go live ready’ site back to FS ahead of go live to allow one day of accessibility checks to the sections for go live.
Post go live Frank will support a week long warranty period where final amends, within scope, can be completed.
A handover into Production Support will be facilitated via a conference call during the warranty period. The ‘Frank’ Production support guide will be supplied.
*See Change Control process slide

## Slide 10: Milestones – Page 1
Public Facing |  |  | 
# | Owner | Description | Deadline
1 | CP HT | Provide social media handles Provide regions for the find a service search page | 27th January 2023
2 | CP HT | Provide default email address for feedback form | 2nd February 2023
3 | CP HT | Confirm domain name registered with the NHS DNS team – Email address provided on basecamp | 13th February 2023
4 | CP HT | Supply IP address to the DNS team – CP HT to endorse the request | 14th February 2023
5 | FS/CP HT | Provide site wide administrator names and email addresses | 27th February 2023
6 | FS/CP HT | Show & Tell + Training - Date & Time TBC | 28th February 2023
7 | FS | Hand site over for content upload | 1st March 2023
8 | FS | Complete content upload and hand site back for final accessibility – 12 Weeks | 24th May 2023
9 | CP HT | Hand site over for UAT – 5 hours of support available | 26th May 2023
10 | CP HT | Site approved for go live | 1st June 2023
11 | FS/CP HT | Go live – Domain TBC Google analytics – CP HT to have a google registered email available or send the measurement/tracking ID from own dashboard SSL Certificate - TBC | 5th June 2023
12 | FS/CP HT | Production support handover call | 6th June 2023
13 | FS | End of warranty period – 5 hours support | 12th June 2023

## Slide 11: Change Control Process
Change actioned
Service Manager Advises Client of estimate
PO Raised by Client (if applicable)
CR Closed
IA & Estimating Completed
IA Scheduled
Service Manager Engaged
Advise client IA to be completed
Requirement change raised
Client Approval
In scope
Yes
No
CR Scheduled into Project
Yes
No

## Slide 12: Project Tools
Frank promotes the use of ‘Basecamp’.
Basecamp allows both FS & CP HT to communicate within one area meaning that we mitigate the risk of losing information via the use of normal email.
All documents and content is to be uploaded by CP HT into their project space within Basecamp.
The following persons have been allocated access and further colleagues can be added by FS on request:
Basecamp Members
Bhesme Nimo

## Slide 13: Retrospective
Frank are passionate about continually improving the service we offer to our clients. One of the most effective ways for us to achieve this objective is to carry out a retrospective review of the project following Go Live.
Frank recommends that any feedback, which can wait until the end of the project, is gathered as it arises by CP HT.
A mutually convenient meeting will be scheduled to review the feedback.

## Slide 14: Outstanding Discussion/Decision
*See Open Actions

## Slide 15: Glossary of Terms
Acronym | Description
IA | Impact Assessment
URL | Uniform Resource Locator
CP HT | Cambridgeshire & Peterborough Healthier Together
FS | Frank Studio
UAT | User Acceptance Testing
CMS | Content Management System
CR | Change Request
PO | Purchase Order
FSP | Functional Specification

## Slide 16: Frank Contacts
Name | Details
Megan Cooper | megan@frankdesignltd.co.uk 0161 955 3502
Mike Smith | mike@frankdesignltd.co.uk 0161 955 3502 Mobile: 07584045979
Harry Gopsill | harry@frankdesignltd.co.uk 0161 955 3502
Jamie Wise | Jamie@frankdesignltd.co.uk 01582 345574 Mobile: 07823443217
Holly Dutton | Holly@frankdesignltd.co.uk 0161 955 3502